## Sheet1
Test Cases Deck Project: DemoBlaze Sample Project Analyst: Jan Daniel Jurado Repository:
Total
[6 empty] | Scenarios Designed |  |  | 10
[6 empty] | Total Executions |  |  | 5
[6 empty] | Total Successful Executions |  |  | 5
[6 empty] | Total Failed Executions |  |  | 0
[6 empty] | Pending Executions |  |  | 5
[6 empty] | Total Effort Executed |  |  | 50% | [16 empty] | Successful
[6 empty] | Total Advance |  |  | 50% | [16 empty] | Failed
[6 empty] | Satisfactory advance |  |  | 50% | [16 empty] | Pending
[9 empty] | Execution 1 | Execution 2 | Execution 3 | Execution 4 | Execution 5
[6 empty] | Scenarios Designed |  |  | 10 | 10 | 10 | 10 | 10
[6 empty] | Total Executions |  |  | 5 | 0 | 0 | 0 | 0 | [12 empty] | Exitoso
[6 empty] | Total Successful Executions |  |  | 5 | 0 | 0 | 0 | 0 | [12 empty] | Fallido
[6 empty] | Total Failed Executions |  |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Pendiente
[6 empty] | Total Advance |  |  | 50% | 0% | 0% | 0% | 0%
[6 empty] | Satisfactory advance |  |  | 50% | 0% | 0% | 0% | 0%
Sprint | Epic | User Story | Criteria of Acceptance | Preconditions | Test Case | Scenario description | Expected Result | Title | Execution | Environment | Date | Execution 2 | Environment | Date | Ejecución 3 | Environment | Date | Ejecución 4 | Environment | Date | Regresion PO | Environment | Date | Results | Obs
|  | As a user I want to Sign Up on the website | User can Sign Up on the website | 1. Open Website URL | 1 | 1. Load the website. 2. Click on Sign Up button. 3. Fill in the form. 4. Click on Sign Up 5. Alert will appear as confirmation | User has a new account to log in into the Website | SignUp Test | Successful | [14 empty] | OK
|  | As a user I want to LogIn on the website | User can Log In with username and password | 1. Open Website URL 2. Have Signed In on the WebSite | 2 | 1. Load the website. 2. Click on Log In button. 3. Fill in the form with username and password. 4. Click on Log In. 5. Confirm if username appears on the website | User can Log In into the account | LogIn Test | Successful | [14 empty] | OK
|  | As a user I want to navigate through the carrousel to see featured products | User can use navigate through carrousel | 1. Open Website URL 2. Have Loged In on the WebSite. | 3 | 1. Load the website. 2. Log in on the website. 3. Use arrow left or right to navigate through carrousel. | User can navigate through the carrousel | Carrousel Test | Pending | [14 empty] | PENDING
|  | As a user I want to use the contact form to get support | User can use contact form to get support | 1. Open Website URL 2. Have Loged In on the WebSite. | 4 | 1. Load the website. 2. Log in on the website. 3. Click on contact. 4. Fill the form. 5. Validate the success message | User can use contact form | Contact Form | Successful | [14 empty] | OK
|  | As a user I wanto to navigate through "Phones" category menu | User can navigate through the "Phones" category menu | 1. Open Website URL 2. Have Loged In on the WebSite. | 5 | 1. Load the website. 2. Log in on the website. 3. Click on Phones Button. 4. Check that appear elements of all categories | User can navigate through the "Phones" category | Category Phones | Successful | [14 empty] | OK
|  | As a user I want to navigate through "Laptops" category menu | User can navigate through the "Laptops" category menu | 1. Open Website URL 2. Have Loged In on the WebSite. | 6 | 1. Load the website. 2. Log in on the website. 3. Click on Laptops Button. 4. Check that appear elements of all categories | User can navigate through the "Laptops" category | Category Laptops | Successful | [14 empty] | OK
|  | As a user I want to navigate through "Monitors" category menu | User can navigate through the "Monitors" category menu | 1. Open Website URL 2. Have Loged In on the WebSite. | 7 | 1. Load the website. 2. Log in on the website. 3. Click on Monitors Button. 4. Check that appear elements of all categories | User can navigate through the "Monitors" category | Category Monitors | Pending | [14 empty] | PENDING
|  | As a user I want to add a product to the cart | User can follow steps to add a product to the cart | 1. Open Website URL 2. Have Loged In on the WebSite. | 8 | 1. Load the website. 2. Log in on the website. 3. Click on any product. 4. Click on add to cart. 5. Confirm added to cart alert. 6. Validate if product appears on the cart | User can add products to the cart | AddingProducts | Pending | [14 empty] | PENDING
|  | As a user I want to delete items from the cart | User can delete products on the cart | 1. Open Website URL 2. Have Loged In on the WebSite. 3. Have products added on the cart. | 9 | 1. Load the website. 2. Log in on the website. 3. Click on cart. 4. Check number of products in the cart. 5. Click on the delete button. 6. Confirm item has been deleted | User can delete products on the cart | DeletingProducts | Pending | [14 empty] | PENDING
|  | As a user I want to purchase a product stored on the cart | User can purchase products added to the cart | 1. Open Website URL 2. Have Loged In on the WebSite. 3. Have products added on the cart. | 10 | 1. Load the website. 2. Log in on the website. 3. Click on cart. 4. Click on place order. 5. Fill in the form. 6. Click on purchase. 7. Accept the alert. 8. Return to HomePage | User can pruchase Items | Buying Items | Pending | [14 empty] | PENDING
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE